Account Success & Renewal Plan

Scaled Customer Success — a sample for Harvey  ·  prepared by Alex Donnelly

Illustrative work sample built for the Scaled Customer Success Manager application. The customer below is fictional; figures are illustrative and not based on Harvey’s actual pricing or data.

ACCOUNT SNAPSHOT

| Field | Detail |
| --- | --- |
| Customer | Meridian & Cole LLP — ~220-lawyer business-litigation & corporate firm (fictional) |
| Segment | Scaled (pooled / digital-led CS) · 180 licensed seats |
| Contract | 12-month term · renews 31 Mar 2027 · single practice-group entry point (Litigation) |
| Stakeholders | Exec sponsor: COO · Champion: Director of Practice Innovation · Power users: 6 litigation associates |
| Primary use cases | Document review & summarization, first-draft research memos, deposition prep |
| Targets | Gross retention 100% · Net revenue retention 120% (expand to Corporate + add seats) |

HOW I’D DEFINE AND DRIVE SUCCESS

Success for a scaled account is value realized, on repeat: usage that becomes a daily habit, documented ROI the sponsor can defend, and a renewal that grows. Adoption is the leading indicator — so I run this account on a simple loop: drive adoption → evidence the value → de-risk the renewal early → expand on proof. At scale, that means productized, one-to-many enablement (self-serve onboarding, office hours, use-case templates) reserved high-touch only for the moments that move the number.

LIFECYCLE PLAN & MILESTONES

| Phase | Window | Focus & milestones | Success metric |
| --- | --- | --- | --- |
| Onboard | Days 0–30 | Provisioning, exec kickoff, champion enablement, first 2 workflows live | ≥70% of seats activated; first value moment logged |
| Adopt | Days 31–90 | Scaled enablement (office hours, self-serve path, templates); first value review | ≥50% weekly active users; 3+ workflows in regular use |
| Realize value | Days 90–180 | Quantify ROI (hours saved, matters touched); exec QBR; capture proof points | Documented ROI; sponsor-level QBR delivered |
| Renew & expand | Days 180–365 | Open renewal early (T-120); pilot Corporate group; propose seat add + multiyear | Renewal closed; NRR ≥ 120% |

HEALTH SCORING & CHURN SIGNALS

| Signal | Healthy (green) | At-risk (red) | Intervention play |
| --- | --- | --- | --- |
| Adoption | WAU ≥ 50%, steady | WAU < 25% or falling 3 wks | Targeted re-onboarding; champion co-hosts a use-case office hour |
| Breadth | 3+ workflows, 2+ teams | Single workflow, 1 user pocket | Map a second high-value workflow; enable an adjacent team |
| Sentiment | Champion advocates | Champion quiet / NPS drop | Exec check-in; surface and close top friction items |
| Champion | Engaged, has budget voice | Champion departs / reorg | Multi-thread to 2–3 new stakeholders fast |
| Commercial | On track, value shown | No ROI story by T-120 | Build the value review now; reset success plan with sponsor |

EXPANSION TRIGGERS (NRR)

- Seat utilization > 85% sustained → propose a seat add before users hit the cap.

- A second practice group asks for access (Corporate) → scoped pilot → cross-sell.

- New high-value use case adopted → land/expand into the team that owns it.

- Client-driven demand or firm headcount growth → multiyear + volume conversation.

RENEWAL MOTION (DATA-DRIVEN CADENCE)

- T-120: open internal renewal review; confirm ROI story and risks; align with Sales.

- T-90: deliver value review / QBR to sponsor; pre-frame renewal + expansion.

- T-60: paper the renewal and expansion proposal; resolve procurement early.

- T-30: confirm signature; schedule the next-term success plan and kickoff.

Operating cadence: weekly health-metric scan across the book · monthly champion check-in + open office hours · quarterly value review / QBR.